## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Deploy Fusion
PROJECT ID | IP -5558
PROJECT MANAGER | Mohammed Umar
PROJECT SPONSOR | Cloud Counselage
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 13/09/2024 | CI/CD pipeline failures | Technical Issues | Yes | Improve error handling and logging in the pipeline | Enhanced logging and alerts | Mohammed Umar | Solved | Resulted in quicker response time.
2 | 15/09/2024 | Delayed deployment to Vercel | Process Improvement | No | Establish a clearer deployment schedule | Created a deployment calendar | Mohammed Umar | Solved | Improved team coordination.
3 | 20/09/2024 | Inefficient code reviews | Team Collaboration | Yes | Implement peer review checkpoints before merging | Instituted mandatory reviews | Mohammed Umar | Solved | Review process is now effective.
4 | 22/09/2024 | Environment configuration issues | Configuration Management | Yes | Document environment setup in detail | Updated configuration docs | Mohammed Umar | Solved | Reduced setup time for new team members.
5 | 23/09/2024 | Lack of monitoring post-deployment | Monitoring | Yes | Set up monitoring alerts for application performance | Implemented monitoring tools | Mohammed Umar | Solved | Provided insights into application health.