## IAC IP23 - Devops - Project Sch
PROJECT SCHEDULE
DOCUMENT VERSION: 1.0
PROJECT NAME | Deploy Fusion
PROJECT MANAGER | Mohammed Umar (Intern)
PROJECT DELIVERABLE | Web Application Deployment
PROJECT SCOPE | Deploy a web application using CI/CD pipeline
PROJECT START DATE | 2024-09-12
PROJECT END DATE | 26/09/2024
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 | Initiation | Mohammed Umar | 2024-09-12 | 2024-09-12 | 1 | COMPLETED
1.1 | Identify project goals | Mohammed Umar | 2024-12-13 | 2024-12-13 | 1 | COMPLETED
1.2 | Research CI/CD tools | Mohammed Umar | 2024-09-13 | 2024-09-14 | 2 | COMPLETED
1.3 | Create project charter | Mohammed Umar | 2024-09-15 | 2024-09-15 | 1 | COMPLETED
2 | Planning | Mohammed Umar | 2024-09-16 | 2024-09-16 | 1 | COMPLETED
2.1 | Define pipeline structure | Mohammed Umar | 2024-09-16 | 2024-09-17 | 2 | COMPLETED
2.2 | Set up GitHub repository | Mohammed Umar | 2024-09-18 | 2024-09-19 | 2 | COMPLETED
2.3 | Configure Vercel | Mohammed Umar | 2024-09-20 | 2024-09-21 | 2 | COMPLETED
3 | Execution | Mohammed Umar | 2024-09-22 | 2024-09-22 | 1 | COMPLETED
3.1 | Develop application | Mohammed Umar | 2024-09-22 | 2024-09-24 | 3 | COMPLETED
3.2 | Integrate CI/CD pipeline | Mohammed Umar | 2024-09-25 | 2024-09-25 | 1 | COMPLETED
3.3 | Testing | Mohammed Umar | 2024-09-26 | 2024-09-26 | 1 | COMPLETED
3.3.1 | Manual testing | Mohammed Umar | 2024-09-26 | 2024-09-26 | 1 | COMPLETED
3.3.2 | Automation testing | Mohammed Umar | 2024-09-26 | 2024-09-26 | 1 | COMPLETED
4 | Closure | Mohammed Umar | 2024-09-26 | 2024-09-26 | 1 | COMPLETED